## Bikerr Project Plan
Bikerr Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Bikerr | Adam Richard | 2021-01-13 | 2021-04-07 |  | 22.54% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  |  | 32 | 2021-01-13 | 2021-02-03 | 21 | Complete
| User Story Backlog | Deliverable | Derek, Michael | 3 | 2021-01-20 | 2021-02-01 | 12 | Complete
| Release Plan | Deliverables | Derek | 2 | 2021-01-31 | 2021-02-03 | 3 | Complete
| Software Architecture Document | Deliverables | Adam, Jamil | 3 | 2021-01-13 | 2021-02-03 | 21 | Complete
| Risk Assessment & Risk Management Plan | Deliverables | James, Ashraf | 2 | 2021-01-13 | 2021-02-03 | 21 | Complete
| UI prototypes | Deliverables | James | 4 | 2021-02-01 | 2021-02-03 | 2 | Complete
| Testing Plan | Deliverables | Shashank, Sacha | 2 | 2021-02-02 | 2021-02-03 | 1 | Complete
| Running prototype | Deliverables | Sacha, Shashank | 4 | 2021-01-20 | 2021-02-03 | 14 | Complete
| Register Personal Accounts | User Story | Sacha, Shashank | 3 | 2021-01-20 | 2021-02-03 | 14 | Complete
| Setup Docker | User Story | Sacha, Shashank | 1 | 2021-01-27 | 2021-02-02 | 6 | Complete
| CRUD Design | User Story | Sacha | 1 | 2021-01-20 | 2021-02-03 | 14 | Complete
| Login Personal Accounts | User Story | Sacha, Shashank | 2 | 2021-01-20 | 2021-02-03 | 14 | Complete
| Automatic Log Out | User Story | Shashank | 2 | 2021-01-30 | 2021-02-01 | 2 | Complete
| Account Password Encryption | User Story | Sacha | 1 | 2021-01-27 | 2021-02-03 | 7 | Complete
| Setup Travis-CI | User Story | Shashank | 1 | 2021-02-02 | 2021-02-03 | 1 | Complete
| Setup Jest | User Story | Shashank | 1 | 2021-02-02 | 2021-02-03 | 1 | Complete
| Sprint 2 |  |  | 48 | 2021-02-04 | 2021-02-24 | 20 | Not Started
| Defects tracking report | Deliverables | Ashraf, Jamil | 5 | 2021-02-04 | 2021-02-14 | 10 | Not Started
| Release Plan For Sprint 3 | Deliverables | Derek | 2 | 2021-02-20 | 2021-02-24 | 4 | Not Started
| UI modeling | Deliverables | James | 3 | 2021-02-18 | 2021-02-20 | 2 | Not Started
| Update SAD, USB, RMP, Testing Plan | Deliverables | Adam | 6 | 2021-02-20 | 2021-02-24 | 4 | Not Started
| Security Personal Accounts | User Story | Shashank | 2 | 2021-02-04 | 2021-02-08 | 4 | Not Started
| Encrypted Data | User Story | Shashank | 3 | 2021-02-04 | 2021-02-08 | 4 | Not Started
| Password Recovery | User Story | Shashank | 2 | 2021-02-04 | 2021-02-08 | 4 | Not Started
| CAPTCHA | User Story | Sacha | 1 | 2021-02-08 | 2021-02-12 | 4 | Not Started
| Log In Limited Attempts | User Story | Sacha, Shashank | 2 | 2021-02-08 | 2021-02-13 | 5 | Not Started
| Permission Access of Different Users | User Story | Shashank | 2 | 2021-02-08 | 2021-02-14 | 6 | Not Started
| Log History | User Story | Ashraf | 3 | 2021-02-14 | 2021-02-20 | 6 | Not Started
| Data Logging | User Story | Michael | 5 | 2021-02-08 | 2021-02-20 | 12 | Not Started
| Error Logging | User Story | Michael | 2 | 2021-02-08 | 2021-02-20 | 12 | Not Started
| MVC Design | User Story | Everyone | 4 | 2021-02-04 | 2021-02-24 | 20 | Not Started
| Update Jest | User Story | Derek, James | 6 | 2021-02-04 | 2021-02-24 | 20 | Not Started
| Sprint 3 |  |  | 62 | 2021-02-25 | 2021-03-17 | 20 | Not Started
| Defects tracking report | Deliverables |  | 5 |  |  | 0 | Not Started
| Release Plan For Sprint 4 | Deliverables |  | 2 |  |  | 0 | Not Started
| UI modeling | Deliverables |  | 3 |  |  | 0 | Not Started
| Update SAD, USB, RMP, Testing Plan | Deliverables |  | 6 |  |  | 0 | Not Started
| Business Account Page | User Story |  | 3 |  |  | 0 | Not Started
| Import/Export to Spreadsheets | User Story |  | 3 |  |  | 0 | Not Started
| Export to PDF | User Story |  | 2 |  |  | 0 | Not Started
| Safe Session Support | User Story |  | 5 |  |  | 0 | Not Started
| Support Concurrent Sessions | User Story |  | 5 |  |  | 0 | Not Started
| Purchasing Manufactured Products | User Story |  | 5 |  |  | 0 | Not Started
| Material List | User Story |  | 3 |  |  | 0 | Not Started
| Track Inventory | User Story |  | 5 |  |  | 0 | Not Started
| Email Notifications | User Story |  | 2 |  |  | 0 | Not Started
| Good UI Design | User Story |  | 5 |  |  | 0 | Not Started
| Tooltips | User Story |  | 1 |  |  | 0 | Not Started
| Help Page | User Story |  | 1 |  |  | 0 | Not Started
| Help Desk | User Story |  | 2 |  |  | 0 | Not Started
| Update Jest | User Story |  | 4 |  |  | 0 | Not Started
| Sprint 4 |  |  | 47 | 2021-03-18 | 2021-04-07 | 20 | Not Started
| Quality Reports | Deliverables |  | 5 |  |  | 0 | Not Started
| Release Plan For Sprint 4 | Deliverables |  | 2 |  |  | 0 | Not Started
| UI modeling | Deliverables |  | 3 |  |  | 0 | Not Started
| Update SAD, USB, RMP, Testing Plan | Deliverables |  | 6 |  |  | 0 | Not Started
| Rating System | User Story |  | 3 |  |  | 0 | Not Started
| Sharing Feature | User Story |  | 3 |  |  | 0 | Not Started
| Production Machinery Communication | User Story |  | 3 |  |  | 0 | Not Started
| Business Process Model | User Story |  | 5 |  |  | 0 | Not Started
| Mobile Friendly | User Story |  | 5 |  |  | 0 | Not Started
| Page Response Time | User Story |  | 1 |  |  | 0 | Not Started
| Test Coverage | User Story |  | 2 |  |  | 0 | Not Started
| Update Travis-CI | User Story |  | 1 |  |  | 0 | Not Started
| Update Jest | User Story |  | 1 |  |  | 0 | Not Started
| Defining products | User Story |  | 1 |  |  | 0 | Not Started
| Multiple Currencies and currency conversion | User Story |  | 2 |  |  | 0 | Not Started
| Process driven work-flow messaging | User Story |  | 4 |  |  | 0 | Not Started
| Sprint 5 |  |  | 14 | 2021-04-08 | 2021-04-20 | 12 | Not Started
| Post-Mortem | Deliverables |  | 7 |  |  | 0 | Not Started
| Self Assessment | Deliverables |  | 7 |  |  | 0 | Not Started