## Bikerr Project Plan
Bikerr Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Bikerr | Adam Richard | 2021-01-13 | 2021-04-07 |  | 70.51% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  |  | 32 | 2021-01-13 | 2021-02-03 | 21 | Complete
| User Story Backlog | Deliverable | Derek, Michael | 3 | 2021-01-20 | 2021-02-01 | 12 | Complete
| Release Plan | Deliverables | Derek | 2 | 2021-01-31 | 2021-02-03 | 3 | Complete
| Software Architecture Document | Deliverables | Adam, Jamil | 3 | 2021-01-13 | 2021-02-03 | 21 | Complete
| Risk Assessment & Risk Management Plan | Deliverables | James, Ashraf | 2 | 2021-01-13 | 2021-02-03 | 21 | Complete
| UI prototypes | Deliverables | James | 4 | 2021-02-01 | 2021-02-03 | 2 | Complete
| Testing Plan | Deliverables | Shashank, Sacha | 2 | 2021-02-02 | 2021-02-03 | 1 | Complete
| Running prototype | Deliverables | Sacha, Shashank | 4 | 2021-01-20 | 2021-02-03 | 14 | Complete
| Register Personal Accounts | User Story [Misc] | Sacha, Shashank | 3 | 2021-01-20 | 2021-02-03 | 14 | Complete
| Setup Docker | User Story [Misc] | Sacha, Shashank | 1 | 2021-01-27 | 2021-02-02 | 6 | Complete
| CRUD Design | User Story [Misc] | Sacha | 1 | 2021-01-20 | 2021-02-03 | 14 | Complete
| Login Personal Accounts | User Story [Misc] | Sacha, Shashank | 2 | 2021-01-20 | 2021-02-03 | 14 | Complete
| Automatic Log Out | User Story [Misc] | Shashank | 2 | 2021-01-30 | 2021-02-01 | 2 | Complete
| Account Password Encryption | User Story [Misc] | Sacha | 1 | 2021-01-27 | 2021-02-03 | 7 | Complete
| Setup Travis-CI | User Story [Misc] | Shashank | 1 | 2021-02-02 | 2021-02-03 | 1 | Complete
| Setup Jest | User Story [Misc] | Shashank | 1 | 2021-02-02 | 2021-02-03 | 1 | Complete
| Sprint 2 |  |  | 54 | 2021-02-04 | 2021-02-24 | 20 | Complete
| Defects tracking report | Deliverables | Ashraf, Jamil | 5 | 2021-02-04 | 2021-02-14 | 10 | Complete
| Release Plan For Sprint 3 | Deliverables | Derek | 2 | 2021-02-20 | 2021-02-24 | 4 | Complete
| UI modeling | Deliverables | James, Adam | 3 | 2021-02-15 | 2021-02-20 | 5 | Complete
| Update SAD, USB, RMP, Testing Plan | Deliverables | Adam, Derek(USB) | 6 | 2021-02-11 | 2021-02-24 | 13 | Complete
| Transportation Tab | Task [Transportation] | Sacha | 2 | 2021-02-08 | 2021-02-11 | 3 | Complete
| Transportation Location | User Story [Transportation] | James, Ashraf | 2 | 2021-02-17 | 2021-02-20 | 3 | Complete
| Track Inventory | User Story [Transportation] | James, Ashraf | 5 | 2021-02-11 | 2021-02-18 | 7 | Complete
| Production Tab | Task [Production] | Sacha | 2 | 2021-02-09 | 2021-02-11 | 2 | Complete
| Interact With Raw Material | User Story [Production] | Derek, Shashank | 3 | 2021-02-12 | 2021-02-16 | 4 | Complete
| Defining products | User Story [Production] | Derek, Shashank | 2 | 2021-02-15 | 2021-02-19 | 4 | Complete
| Material List | User Story [Production] | Michael, Shashank | 3 | 2021-02-13 | 2021-02-16 | 3 | Complete
| Production Inventory | User Story [Production] | Sacha, Shashank | 3 | 2021-02-18 | 2021-02-23 | 5 | Complete
| Sales & Accounting Tab (Finance Tab) | Task [Finance] | Sacha | 1 | 2021-02-10 | 2021-02-11 | 1 | Complete
| Quality Assurance Tab | Task [Quality] | Sacha | 1 | 2021-02-10 | 2021-02-11 | 1 | Complete
| Security Personal Accounts | User Story [Misc] | Shashank, Sacha | 2 | 2021-02-06 | 2021-02-09 | 3 | Complete
| Permission Access of Different Users | User Story [Misc] | Sacha | 2 | 2021-02-09 | 2021-02-11 | 2 | Complete
| Dashboard | User Story [Misc] | Sacha | 2 | 2021-02-20 | 2021-02-23 | 3 | Complete
| MVC Design | User Story [Misc] | Everyone | 4 | 2021-02-04 | 2021-02-11 | 7 | Complete
| Update Jest | User Story [Misc] | Derek, Jamil | 4 | 2021-02-19 | 2021-02-24 | 5 | Complete
| Sprint 3 |  |  | 51 | 2021-02-25 | 2021-03-17 | 20 | Complete
| Defects tracking report | Deliverables | Jamil, Adam | 5 | 2021-03-09 | 2021-03-16 | 7 | Complete
| Release Plan For Sprint 4 | Deliverables | Derek | 2 | 2021-02-26 | 2021-03-02 | 4 | Complete
| UI modeling | Deliverables | James, Adam | 3 | 2021-03-16 | 2021-03-17 | 1 | Complete
| Update SAD, USB, RMP, Testing Plan | Deliverables | Adam, Derek (USB), Shashank (SAD) | 6 | 2021-03-10 | 2021-03-16 | 6 | Complete
| Packaging | User Story [Transportation] | James, Ashraf | 3 | 2021-03-02 | 2021-03-09 | 7 | Complete
| Connect Transport and Production | User Story [Transportation] | James, Ashraf, Shashank, Derek | 3 | 2021-03-12 | 2021-03-15 | 3 | Complete
| Transportaton Temporal | User Story [Transportation] | James, Ashraf | 2 | 2021-03-01 | 2021-03-09 | 8 | Complete
| Production Build Bikes | User Story [Production] | Derek, Shashank | 2 | 2021-03-03 | 2021-03-07 | 4 | Complete
| Procurement | User Story [Finance] | James, Ashraf | 4 | 2021-03-06 | 2021-03-16 | 10 | Complete
| Sales | User Story [Finance] | James, ashraf | 2 | 2021-03-06 | 2021-03-16 | 10 | Complete
| Scheduling | User Story [Production] | Derek | 3 | 2021-03-03 | 2021-03-07 | 4 | Complete
| Quality of Parts | User Story [Quality] | Derek, Shashank | 2 | 2021-02-28 | 2021-03-09 | 9 | Complete
| Track Defects | User Story [Quality] | Derek | 2 | 2021-03-08 | 2021-03-09 | 1 | Complete
| Error Logging | User Story [Misc] | Everyone | 2 | 2021-03-08 | 2021-03-17 | 9 | Complete
| Encrypted Data | User Story [Misc] [Finance] | Shashank | 3 | 2021-03-03 | 2021-03-08 | 5 | Complete
| Help Page | User Story [Misc] | Jamil, James | 1 | 2021-03-15 | 2021-03-17 | 2 | Complete
| Email Notifications | User Story [Misc] | Sacha | 2 | 2021-03-04 | 2021-03-08 | 4 | Complete
| Update Jest | User Story [Misc] | Michael, Sacha, Shashank | 4 | 2021-03-11 | 2021-03-17 | 6 | Complete
| Sprint 4 |  |  | 59 | 2021-03-18 | 2021-04-07 | 20 | Not Started
| Quality Reports | Deliverables | Jamil, Adam | 5 | 2021-03-23 | 2021-03-30 | 7 | Not Started
| Release Plan For Sprint 5 | Deliverables | Derek | 2 | 2021-03-19 | 2021-03-22 | 3 | Not Started
| UI modeling | Deliverables | James, Adam | 3 | 2021-04-05 | 2021-04-07 | 2 | Not Started
| Update SAD, USB, RMP, Testing Plan | Deliverables | Adam, Derek (USB) | 6 | 2021-03-18 | 2021-03-26 | 8 | Not Started
| Production Assembly Line Simulation | User Story [Production] | James, Ashraf | 5 | 2021-03-22 | 2021-03-29 | 7 | Not Started
| Production Machinery Communication | User Story [Production] | Sashank | 3 | 2021-03-28 | 2021-04-01 | 4 | Not Started
| Track Quality data | User Story [Quality] | James, Ashraf | 3 | 2021-03-19 | 2021-03-22 | 3 | Not Started
| Export to PDF | User Story [Finance] | Sacha | 2 | 2021-03-20 | 2021-03-24 | 4 | Not Started | Moved To Sprint 4
| Business Account Page | User Story [Finance] | James | 3 | 2021-03-22 | 2021-03-26 | 4 | Not Started | Moved To Sprint 4
| Accounting | User Story [Finance] | Jamil | 3 | 2021-03-26 | 2021-03-30 | 4 | Not Started | Moved To Sprint 4
| Audit Trails | User Story [Finance] | Sacha | 4 | 2021-03-31 | 2021-04-05 | 5 | Not Started | Moved To Sprint 4
| Planning | User Story [Finance] | James, ashraf | 2 | 2021-03-06 | 2021-03-16 | 10 | Not Started | Moved To Sprint 4
| Mobile Friendly | User Story [Misc] | Shashank | 5 | 2021-03-18 | 2021-03-23 | 5 | Not Started
| Page Response Time | User Story [Misc] | James, Ashraf | 1 | 2021-04-04 | 2021-04-06 | 2 | Not Started
| Tooltips | User Story [Misc] | Derek, Shashank | 1 | 2021-03-22 | 2021-03-24 | 2 | Not Started
| Test Coverage | User Story [Misc] | Shashank | 2 | 2021-04-01 | 2021-04-05 | 4 | Not Started
| UI Testing | User Story [Misc] | Jamil, Sacha | 4 | 2021-03-11 | 2021-03-17 | 6 | Not Started | Moved To Sprint 4
| Update Jest | User Story [Misc] | Jamil, Sacha | 1 | 2021-04-04 | 2021-04-06 | 2 | Not Started
| Process driven work-flow messaging | User Story [Misc] | Michael, Sacha, Shashank | 4 | 2021-03-23 | 2021-03-28 | 5 | Not Started
| Sprint 5 |  |  | 14 | 2021-04-08 | 2021-04-20 | 12 | Not Started
| Post-Mortem | Deliverables |  | 7 | 2021-04-08 | 2021-04-20 | 12 | Not Started
| Self Assessment | Deliverables |  | 7 | 2021-04-08 | 2021-04-20 | 12 | Not Started

## Agile Project Plan TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Product Release | Alex B. | 2022-09-02 | 2022-10-10 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2022-09-03 | 2022-09-13 | 10 | Complete
| Feature 1 |  | Frank C. |  | 2022-09-03 | 2022-09-07 | 4 | Complete
| Feature 2 |  | Jacob S. |  | 2022-09-07 | 2022-09-12 | 5 | Complete
| Feature 3 |  | Jacob S. |  | 2022-09-09 | 2022-09-13 | 4 | Overdue
| Sprint 2 |  | Jacob S. |  | 2022-09-16 | 2022-09-24 | 8 | In Progress
| Feature 4 |  | Alex B. |  | 2022-09-16 | 2022-09-17 | 1 | In Progress
| Feature 5 |  | Frank C. |  | 2022-09-17 | 2022-09-21 | 4 | Not Started
| Feature 6 |  | Shari W. |  | 2022-09-22 | 2022-09-24 | 2 | Not Started
| Sprint 3 |  | Shari W. |  | 2022-09-25 | 2022-10-05 | 10 | Not Started
| Feature 7 |  | Alex B. |  | 2022-09-25 | 2022-09-29 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2022-09-24 | 2022-10-02 | 8 | Not Started
| Feature 9 |  | Jacob S. |  | 2022-10-02 | 2022-10-05 | 3 | Not Started

## -Disclaimer-
Please update this as per your ERP system name and policies you want to adopt