## Simple Safety Risk Register
Risk Tracking Spreadsheet 1.2
RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER | KEY
Brief Summary of the Risk. | Brief Description on Impact if Risk is Left Unmitigated or Unresolved | Rate 1 (LOW) 2(MEDIUM) 3 (HIGH) | Rate 1 (LOW) 2(MEDIUM) 3 (HIGH) | (IMPACT X PROBABILITY) Address the highest first. | Mitigation Actions to be Taken | Who is Responsible for this Risk | LEVEL
Might accidentally run out of machines when deleting them | There is nothing in place preventing a user from deleting all machines at a given location, or all machines at all locations. New machines would need to be added. | 2 | 1 | 2 | Create "Are you sure?" box | Derek Ruiz-Cigana | 1
Token expires prematurely. | The user could be kicked out of the website at any time without a valid or pre-planned reason. | 1 | 1 | 1 | Token features should be regularly tested and verified to be functioning as intended. | Sacha Elkaim | 2
Token expires without logging out the user. | The user would not be logged out potentially lagging the site and impacting performance. It can also lead to a security issue where potentially important information can be displayed on the screen. | 3 | 2 | 6 | Token features should be regularly tested and verified to be functioning as intended. | Sacha Elkaim | 3
User enters invalid data that is accepted. | User enters invalid data that is accepted into certain inputs potentially corrupting the data base and also of displaying false information. | 2 | 2 | 4 | Make sure that all inputs have validation tests to insure only valid information is snet tot he back-end. | Shashank Patel
Abort machine fabrication | Stops whatever the machine is doing and jetisons everything, potentially causing scheduling issues in production. | 3 | 2 | 6 | Include checks to see what machines are functioning and with what items | Michael Takenaka
PO order properly display in the AP tab as well | All POs should also be displayed in the accounts payable tab as they need to be payed by that department. | 3 | 2 | 6 | Rigorous testing, to make sure data is being displayed correctly | Ashraf Khalil
Sales properly display in the AR tab as well | All Sales should also be displayed in the accounts receivable tab as they need to validate payements are received in that department. | 3 | 2 | 6 | Rigorous testing, to make sure data is being displayed correctly | Ashraf Khalil

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.